|  |
| --- |
|  |
|  |
| Appendix 3.1 – Survey Plan of Work |

Contents

[1. General 3](#_Toc126007748)

[2. Plan of Work 3](#_Toc126007749)

1. General

The following critical milestones shall be incorporated in the Survey Plan of Work:

|  |  |  |
| --- | --- | --- |
| Milestone | Milestone month | Comments |
| Survey Plan (Plan of Work) | April 30th, 2023 | The Plan of Work for the Survey must be agreed as part of the Contract signing. |
| Mobilization Completed | June 1st, 2023 | It is expected that mobilization of the survey vessel is completed latest beginning of June 2023 |
| Survey Completed | Latest November 1st, 2023 |  |
| Delivery of Preliminary Survey Report | Latest November 15th, 2023 | Preliminary Report to be delivered to Purchaser mid-November 2023 |
| Comments to preliminary survey report | Latest December 15th, 2023 | Purchaser delivers comments or approval of preliminary report |
| Delivery of Final Survey Report | Latest January 15th, 2024 | Contractor to deliver final survey report |

The Survey Plan of Work shall be made as a Gantt Chart in MS Project.

1. Plan of Work